RESEARCH WORKPLAN

KV Cache Quantization x Privacy

Three-person execution plan for a controlled privacy-utility-bitrate study

Status: Kickoff plan - baseline-first research

Initial model: Llama-3.2-1B-Instruct; immutable revision to be pinned

Initial precisions: FP16, INT8, and INT4

Deadline: Monday, August 31, 2026

Decision: The first deliverable is a trustworthy privacy-utility-bitrate curve, not a new defense. Mathematical design begins only after the baseline reveals a stable phenomenon.

# 1. Research objective

Determine how KV-cache precision changes exact, semantic, and sensitive-information leakage relative to model utility. Quantization is initially treated as a controlled independent variable, not as a privacy mechanism.

The core comparison is paired: the same prompt, checkpoint, seed, generation configuration, cache extraction point, and attack budget must be used at FP16, INT8, and INT4.

# 2. Team allocation

## Person A - Quantization and utility

Primary question. Can the model use a lower-precision cache without losing task performance?

- Pin the model and tokenizer revisions and deterministic generation configuration.

- Implement standardized K/V capture hooks and versioned cache bundles.

- Implement controlled symmetric INT8 and INT4 quantization with recorded scales, zero points, grouping, clipping, and RoPE stage.

- Integrate the quantized cache into autoregressive attention so utility is measured on a cache the model actually reads.

- Measure logit divergence, generation agreement, QA, long-context retrieval, memory, and latency.

Acceptance gate: Repeated FP16 extraction is tensor-identical and metadata-complete.

Acceptance gate: One command reproduces the pilot online quantized-cache utility result.

## Person B - Leakage and attacks

Primary question. How much information can an informed attacker recover at each precision?

- Reproduce a reliable FP16 reconstruction attack before interpreting quantization.

- Implement token, semantic, and sensitive-attribute leakage objectives.

- Evaluate both naive and quantization-adaptive attackers that know the quantizer and scales.

- Hold attack initialization, budget, stopping rule, and evaluation code constant across precisions.

- Write per-sample outputs with convergence diagnostics and later lead K-versus-V and layer/head analyses.

Acceptance gate: FP16 leakage is stable and exceeds a control baseline.

Acceptance gate: Adaptive attacks consume quantized metadata correctly; a format mismatch cannot explain the result.

## Person C - Dataset, evaluation, and reproducibility

Primary question. Are the observed differences valid, statistically meaningful, and reproducible?

- Create controlled synthetic public, personal, financial, medical, and confidential prompt categories.

- Predefine secret spans, attribute labels, immutable splits, and dataset versions.

- Maintain experiment manifests and validate paired comparisons across precisions.

- Aggregate per-sample leakage and utility records, confidence intervals, failure cases, and final figures.

- Audit cache schemas and later lead information-concentration, RAG, and multimodal extensions after the text baseline passes.

Acceptance gate: The dataset manifest, threat model, metrics, and cache schema are frozen before the final paired run.

Acceptance gate: Every aggregate is traceable to per-sample records and a reproducible command.

# 3. Shared interface contract

Person C publishes prompt manifests. Person A produces versioned cache bundles. Person B consumes those bundles and produces per-sample attack records. Person C joins leakage and utility outputs through prompt ID, precision, and experiment ID.

- Model/tokenizer revision, code revision, prompt ID, token IDs, and seed.

- Layer, KV-head, sequence, and head-dimension layout.

- Capture stage and whether RoPE has already been applied to keys.

- Original dtype, target precision, quantization granularity, scale, zero point, and clipping.

- Whether the quantized cache was used during inference or supplied only to the attacker.

# 4. Threat model and attack levels

Attacker has: Leaked KV cache, model architecture and weights, tokenizer, quantization algorithm, grouping, clipping rule, scales, and zero points.

Attacker lacks: Victim prompt, victim response, and secret labels.

- Naive attack - the FP16 attack is run without quantization-specific adaptation.

- Adaptive attack - the attacker dequantizes or explicitly optimizes against the quantized representation.

- Oracle diagnostic - optional upper-bound condition, always labeled unrealistic and never presented as an attack success.

Claim boundary. A drop in naive-attack performance is not evidence of privacy protection. Any security claim requires an adaptive attacker evaluated under the same model, prompts, precision, and budget.

# 5. Parallel execution

All three people begin immediately and work concurrently. Person C publishes the smoke-test manifest and experiment identifiers; Person A and Person B independently produce cache/utility and attack outputs using those identifiers; Person C continuously validates compatibility and merges completed results.

- Person C publishes the shared smoke-test manifest before the final paired run.

- Person A and Person B do not wait for each other after the manifest and cache schema are fixed.

- A result enters the Monday report only when its reproduction command and limitations are recorded.

# 6. Metrics and experimental distinction

## Privacy pipeline

Capture an FP16 cache once, quantize the same tensors at each precision, and supply those representations to the attacker.

## Utility pipeline

Run autoregressive inference while attention actually reads the quantized cache. Post-hoc quantization of an unused cache cannot measure utility degradation.

| Dimension | Required measures | Why separate |
| --- | --- | --- |
| Exact leakage | Token accuracy, sequence accuracy, edit distance | Tests literal recovery |
| Semantic leakage | Embedding similarity plus inspectable examples | Captures meaning after wording changes |
| Sensitive leakage | Attribute classification and secret-span recovery | Measures the privacy harm directly |
| Utility | Logit divergence, generation agreement, QA, retrieval | Separates privacy changes from model damage |
| Efficiency | Cache bytes, latency, throughput | Confirms a real compression benefit |

# 7. Review gates

- Protocol gate - no experiments before the model revision, threat model, cache schema, and dataset version are frozen.

- FP16 gate - quantization results are not interpreted until the FP16 attack is reliable.

- Adaptive-attack gate - naive degradation cannot be called a privacy benefit.

- Utility gate - utility requires an actually used quantized cache.

- Claim gate - confidence intervals, category results, and failure cases precede conclusions.

# 8. Repository workflow

Main branch: Reviewed integration only.

Person A branches: feat/quantization-*

Person B branches: feat/attacks-*

Person C branches: feat/evaluation-*

Every experiment-changing pull request records the pinned revisions, seed, prompt-set version, cache schema, quantization parameters, inference/attack distinction, reproduction command, and verification performed.

# 9. Monday submission package

- One end-to-end FP16 smoke test.

- Controlled INT8 and INT4 conversion of the same caches.

- At least one adaptive leakage attack across the available precisions.

- An online quantized-cache utility smoke test, or an explicit blocker if integration is incomplete.

- Per-sample machine-readable results and initial privacy/utility versus precision plots.

- A concise limitations section separating completed results from planned work.

This is a pilot submission. It does not need to prove a new defense by Monday.

# 10. Later mathematical direction

Only after the pilot reveals a stable phenomenon should the group optimize a privacy-aware quantizer. A candidate constrained objective is:

min_Q L_utility(Q) + lambda_c R(Q) - lambda_p L_adaptive_attack(Q)

Here R(Q) is bitrate and the privacy term is evaluated against a strong adaptive attacker. Any proposed method must be compared with simple uniform, per-channel, and per-head quantization at matched bitrate and utility.

# 11. Immediate kickoff checklist

- Assign names to Persons A, B, and C.

- Pin the model and tokenizer revisions.

- Approve the synthetic-data policy and pilot size.

- Finalize the cache bundle schema.

- Select the first FP16 reconstruction attack.

- Create one end-to-end smoke test using five prompts.

- Hold the first integration review after the smoke test passes.